## Slide 1
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes
Omar Mubarak | Project Sponsor, Owner | H | L | Manager of the group, incredibly busy schedule. Responsible for the overall profitability and reputation of the group.
Peta Tsosie | Project Lead, Project Manager | M | H | Project Manager
Deanna Coleman | Director of Operations | H | H | Dive in projects and work directly with the involved. Has high expectations for excellence
Carter Ward | Executive Chief | H | H | Has a final say on menu choices, responsible for overseeing all other chefs employed by the restaurant.
Gilly Tyson | General Manager (North) | M | M | Resource for training and providing general input on operations.
Alex Schmidt | General Manager (Downtown) | M | M | Resource for training and providing general input on operations.
Nia Williams | General Manager (Waterfront) | M | M | Resource for training and providing general input on operations.
Zane Dutchman | Kitchen Manager (North) | L | M | Responsible for operations and administrative tasks, controlling costs and managing labor.
Larissa Stein | Kitchen Manager (Downtown) | L | M | Responsible for operations and administrative tasks, controlling costs and managing labor.
Seydou Diallo | Restaurant Technology Consultant | L | L | Determines client needs, highlights technology processes and improve guest experience.
Stakeholder Analysis

## Slide 2
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Omar
Owner
Drag each stakeholder’s box to the appropriate place on the power-interest grid
Deanna
Director of Operations
Carter
Exec. Chef
Gilly
GM - North
Alex
GM - Downtown
Zane
Kitchen Manager - North
Larissa
Kitchen Manager - Downtown
Seydou
Restaurant Consultant
Interest
med
Nia
General Manager - Waterfront